## Sheet1
TaskID | TaskName | TaskDescription | MandatorySkills | PreferredSkills | EmployeesNeeded | TaskDifficulty | AssignedEmployees | Project | StartDate | EndDate
1 | Design UI | Create user interface mockups and wireframes | UI/UX Design | Graphic Design | 3 | Intermediate | 0 | Web Development | 2024-01-01 | 2024-03-31
2 | Implement Backend | Develop server-side logic and APIs | Node.js | Express.js | 2 | Advanced | 0 | Web Development | 2024-01-15 | 2024-05-15
3 | Database Design | Design and implement database schema | SQL | Database Management | 1 | Intermediate | 0 | Web Development | 2024-02-01 | 2024-07-01
4 | Mobile App Development | Build mobile application for iOS and Android | React Native | Mobile Development | 4 | Advanced | 0 | Mobile App | 2024-01-10 | 2024-06-30
5 | Testing and QA | Conduct thorough testing of the application | Software Testing | Quality Assurance | 2 | Intermediate | 0 | Quality Assurance | 2024-01-20 | 2024-04-30
6 | Project Planning | Create project plans and timelines | Project Management | Agile Methodology | 1 | Beginner | 0 | Project Management | 2024-02-05 | 2024-05-31
7 | Data Analysis | Analyze and interpret project-related data | Data Analysis | Data Visualization | 2 | Intermediate | 0 | Data Analysis | 2024-01-25 | 2024-07-15
8 | Frontend Development | Implement client-side logic and user interface | HTML | JavaScript | 3 | Advanced | 0 | Web Development | 2024-02-10 | 2024-06-10
9 | Network Configuration | Set up and configure network infrastructure | Cisco Networking | Network Security | 1 | Intermediate | 0 | Network Infrastructure | 2024-01-15 | 2024-04-30
10 | Content Creation | Generate content for marketing and communication | Content Writing | Graphic Design | 2 | Beginner | 0 | Marketing | 2024-01-05 | 2024-05-31
11 | System Integration | Integrate different software systems | System Integration | API Integration | 2 | Advanced | 0 | System Integration | 2024-02-01 | 2024-06-30
12 | UI Testing | Perform user interface testing | Software Testing | UI/UX Design | 1 | Intermediate | 0 | Quality Assurance | 2024-02-15 | 2024-05-15
13 | Security Audit | Conduct security assessments and audits | Cybersecurity | Penetration Testing | 2 | Advanced | 0 | Security | 2024-01-10 | 2024-07-10
14 | Content Management | Manage and organize project-related content | Content Management Systems | Documentation | 1 | Beginner | 0 | Content Management | 2024-01-20 | 2024-06-15
15 | Mobile App Testing | Test and debug mobile applications | Mobile Testing | Software Testing | 2 | Intermediate | 0 | Quality Assurance | 2024-02-05 | 2024-05-31
16 | DevOps Automation | Automate deployment and operations tasks | DevOps | Scripting | 3 | Advanced | 0 | DevOps | 2024-01-15 | 2024-06-30
17 | Machine Learning | Implement machine learning algorithms and models | Machine Learning | Data Science | 2 | Advanced | 0 | Machine Learning | 2024-02-01 | 2024-07-15
18 | Customer Support | Provide customer support and assistance | Customer Service | Communication Skills | 2 | Beginner | 0 | Customer Support | 2024-01-25 | 2024-05-31
19 | Cloud Infrastructure | Manage and configure cloud infrastructure | AWS | Azure | 1 | Intermediate | 0 | Cloud Infrastructure | 2024-01-10 | 2024-04-30
20 | Scrum Master | Facilitate agile scrum processes | Scrum | Agile Methodology | 1 | Beginner | 0 | Project Management | 2024-01-05 | 2024-05-31